## Sheet1
JBoss.org JIRA
Displaying issues as at 08/Jan/07 03:10 AM.
Issue Type	Key	Summary	Fix Version/s	Assign To	Reporter	Priority	Votes	Status	Resolution	Component/s	Created	Updated
Bug	JBWS-1428	Java to WSDL - Arrays defined with indexed properties within value type are skipped when generating the WSDL	jbossws-1.2.0	Darran Lofthouse	Darran Lofthouse	Major	0	Coding In Progress	UNRESOLVED	wstools	14/Dec/06 06:03 AM	08/Jan/07 02:20 AM
Bug	JBWS-1260	WSDL To Java - Parameter unwrapping fails for a lot of scenarios.	jbossws-1.2.0	Darran Lofthouse	Ole Matzura	Major	5	Coding In Progress	UNRESOLVED	wstools	30/Sep/06 09:32 AM	08/Jan/07 02:20 AM
Bug	JBWS-1328	Client security configuration not loaded when client deployed with issolated classloader.	jbossws-1.2.0	Darran Lofthouse	Thomas Diesler	Major	0	Open	UNRESOLVED	ws-security	04/Nov/06 05:46 PM	08/Jan/07 02:29 AM
Feature Request	JBWS-434	Support sequences of anys	jbossws-1.2.0	Heiko Braun	Thomas Diesler	Critical	3	Reopened	UNRESOLVED	jaxrpc	30/Sep/05 04:46 AM	08/Jan/07 03:10 AM
Task	JBWS-1084	Cleanup shared schema references	jbossws-1.2.0	Heiko Braun	Heiko Braun	Major	0	Open	UNRESOLVED	jaxrpc	19/Jul/06 09:11 AM	08/Jan/07 02:20 AM
Task	JBWS-1100	Move WS-Eventing to updated wsa schema	jbossws-1.2.0	Heiko Braun	Heiko Braun	Major	0	Open	UNRESOLVED	ws-eventing	24/Jul/06 11:26 AM	08/Jan/07 02:20 AM
Bug	JBWS-1333	Fix marshalling of null values in base64Binary, hexBinary	jbossws-1.2.0	Heiko Braun	Thomas Diesler	Major	0	Reopened	UNRESOLVED	jaxrpc	05/Nov/06 02:02 PM	08/Jan/07 02:20 AM
Patch	JBWS-1399	JBWS-1178 implementation trouble	jbossws-1.2.0	Heiko Braun	Stefano Maestri	Major	1	Open	UNRESOLVED		23/Nov/06 08:32 AM	08/Jan/07 02:20 AM
Feature Request	JBWS-1406	WS-Eventing: event notification failure	jbossws-1.2.0	Heiko Braun	Alessio Soldano	Major	0	Open	UNRESOLVED	ws-eventing	30/Nov/06 10:51 AM	08/Jan/07 02:20 AM
Task	JBWS-1429	Cleanup PortComponent annotation	jbossws-1.2.0	Heiko Braun	Heiko Braun	Major	0	Open	UNRESOLVED		18/Dec/06 07:37 AM	08/Jan/07 02:29 AM
Task	JBWS-1434	Client programming: Add property API at Service level similiar to StubExt.	jbossws-1.2.0	Heiko Braun	Heiko Braun	Major	0	Open	UNRESOLVED		21/Dec/06 05:26 AM	08/Jan/07 02:30 AM
Feature Request	JBWS-1388	Notification validation before dispatch	jbossws-1.2.0	Heiko Braun	Heiko Braun	Major	0	Open	UNRESOLVED	ws-eventing	16/Nov/06 02:59 PM	08/Jan/07 02:38 AM
Feature Request	JBWS-652	Add JAAS certificate authentication support to ws-security implementation	jbossws-1.2.0	Jason T. Greene	Jason T. Greene	Major	3	Open	UNRESOLVED	ws-security	14/Jan/06 10:33 AM	08/Jan/07 02:20 AM
Bug	JBWS-1394	Fix OneWayJava2WSDLTestCase	jbossws-1.2.0	Jason T. Greene	Thomas Diesler	Major	0	Open	UNRESOLVED	wstools	21/Nov/06 07:37 AM	08/Jan/07 02:29 AM
Task	JBWS-1294	Add support for mapping async methods	jbossws-1.2.0	Jason T. Greene	Jason T. Greene	Major	0	Open	UNRESOLVED	jaxws	11/Oct/06 12:58 PM	08/Jan/07 02:30 AM
Bug	JBWS-1336	JAXWSDeployerJSE throws NPE	jbossws-1.2.0	Thomas Diesler	Anil Saldhana	Critical	0	Open	UNRESOLVED	jaxws	07/Nov/06 03:34 PM	08/Jan/07 02:20 AM
Bug	JBWS-1385	schema import fails for relative schemaLocation	jbossws-1.2.0	Thomas Diesler	Thomas Diesler	Major	0	Open	UNRESOLVED	jaxrpc	16/Nov/06 05:44 AM	08/Jan/07 02:20 AM
Bug	JBWS-1408	NPE when jbossws.sar is not expanded	jbossws-1.2.0	Thomas Diesler	Thomas Diesler	Major	0	Open	UNRESOLVED		05/Dec/06 02:12 PM	08/Jan/07 02:20 AM
Sub-task	JBWS-1274	JBWS-1273	jbossws-1.2.0	Thomas Diesler	Thomas Diesler	Major	0	Open	UNRESOLVED	jaxrpc	04/Oct/06 05:43 AM	08/Jan/07 02:20 AM
		jboss-4.0.4.GA (jdk1.4)
Bug	JBWS-1386	ComplexType with base64Binary property	jbossws-1.2.0	Thomas Diesler	Thomas Diesler	Major	0	Open	UNRESOLVED	jaxrpc	16/Nov/06 07:06 AM	08/Jan/07 02:20 AM
Task	JBWS-1420	Change jaxrpc-mapping document location	jbossws-1.2.0	Thomas Diesler	Thomas Diesler	Major	0	Open	UNRESOLVED	wstools	12/Dec/06 07:19 AM	08/Jan/07 02:20 AM
Bug	JBWS-810	Simple type with restriction	jbossws-1.2.0	Thomas Diesler	Thomas Diesler	Major	0	Reopened	UNRESOLVED	wstools	10/Apr/06 05:51 PM	08/Jan/07 02:20 AM
Bug	JBWS-1415	IAE in WSDLToJava.unwrapRequestParticles	jbossws-1.2.0	Thomas Diesler	Thomas Diesler	Major	0	Open	UNRESOLVED	wstools	07/Dec/06 06:15 PM	08/Jan/07 02:20 AM
Bug	JBWS-1383	NPE when doc/lit message uses simple type in response	jbossws-1.2.0	Thomas Diesler	Thomas Diesler	Major	0	Open	UNRESOLVED	jaxrpc	16/Nov/06 04:59 AM	08/Jan/07 02:20 AM
Bug	JBWS-1407	Premature end of File exception on createMessage	jbossws-1.2.0	Thomas Diesler	Thomas Diesler	Major	0	Open	UNRESOLVED		05/Dec/06 01:21 PM	08/Jan/07 02:20 AM
Feature Request	JBWS-1381	Disable HTTP chunking for J2ME client s	jbossws-1.2.0	Thomas Diesler	Thomas Diesler	Major	1	Open	UNRESOLVED	jaxrpc	16/Nov/06 04:30 AM	08/Jan/07 02:20 AM
Bug	JBWS-800	ClassCastException when trying to marshal a SybaseTimestamp	jbossws-1.2.0	Thomas Diesler	Chris Baxter	Major	5	Open	UNRESOLVED	jaxrpc	07/Apr/06 03:39 PM	08/Jan/07 02:20 AM
Task	JBWS-1273	Release jbossws-1.2.0.GA binary	jbossws-1.2.0	Thomas Diesler	Thomas Diesler	Major	1	Open	UNRESOLVED	jaxrpc	04/Oct/06 05:43 AM	08/Jan/07 02:20 AM
Bug	JBWS-1384	Cannot obtain java/xml type mapping for attachmet part	jbossws-1.2.0	Thomas Diesler	Thomas Diesler	Major	0	Open	UNRESOLVED	jaxrpc	16/Nov/06 05:04 AM	08/Jan/07 02:20 AM
Bug	JBWS-1427	NPE in WSDL11Reader.processOperationInput	jbossws-1.2.0	Thomas Diesler	Thomas Diesler	Major	0	Open	UNRESOLVED		13/Dec/06 10:24 AM	08/Jan/07 02:20 AM
Bug	JBWS-1339	@Security domain vs. <security-domain>	jbossws-1.2.0	Thomas Diesler	Thomas Diesler	Major	0	Open	UNRESOLVED	jaxws	08/Nov/06 11:29 PM	08/Jan/07 02:20 AM
Sub-task	JBWS-1275	JBWS-1273	jbossws-1.2.0	Thomas Diesler	Thomas Diesler	Major	0	Open	UNRESOLVED	jaxrpc	04/Oct/06 05:43 AM	08/Jan/07 02:20 AM
		jboss-4.0.x (jdk1.5)
Sub-task	JBWS-1276	JBWS-1273	jbossws-1.2.0	Thomas Diesler	Thomas Diesler	Major	0	Open	UNRESOLVED	jaxrpc	04/Oct/06 05:43 AM	08/Jan/07 02:20 AM
		apache-tomcat (jdk1.5)
Task	JBWS-723	Protect access to wsdl	jbossws-1.2.0	Thomas Diesler	Thomas Diesler	Major	1	Open	UNRESOLVED	jaxrpc	05/Mar/06 12:02 PM	08/Jan/07 02:20 AM
Bug	JBWS-1410	NumberFormatException From StubExt.PROPERTY_CLIENT_TIMEOUT	jbossws-1.2.0	Thomas Diesler	Thomas Diesler	Major	0	Open	UNRESOLVED		05/Dec/06 04:17 PM	08/Jan/07 02:20 AM
Bug	JBWS-1393	Problem interpreting messages with attachment when confronted with no <start> header	jbossws-1.2.0	Thomas Diesler	Romeu Figueira	Major	0	Open	UNRESOLVED		20/Nov/06 11:32 AM	08/Jan/07 02:20 AM
Sub-task	JBWS-1277	JBWS-1273	jbossws-1.2.0	Thomas Diesler	Thomas Diesler	Major	0	Open	UNRESOLVED	jaxrpc	04/Oct/06 05:43 AM	08/Jan/07 02:20 AM
		Pass CTS for jaxr, jaxrpc, saaj, webservice
Feature Request	JBWS-1157	Clarify usage of @WebParam vs. @RequestWrapper	jbossws-1.2.0	Thomas Diesler	Thomas Diesler	Major	1	Open	UNRESOLVED	jaxws	31/Aug/06 03:02 AM	08/Jan/07 02:30 AM
Feature Request	JBWS-1192	Examples for JSR181 EJB Endpoints: show how to use a JavaBean as an operations's argument or return value	jbossws-1.2.0	Thomas Diesler	Juergen Zimmermann	Major	0	Open	UNRESOLVED	documentation	13/Sep/06 04:17 AM	08/Jan/07 02:30 AM
Bug	JBWS-1285	java.lang.NullPointerException is thrown when the soap encoded array size is 0 on the return path	jbossws-1.2.0	Thomas Diesler	George Gan	Major	0	Open	UNRESOLVED	jaxrpc	05/Oct/06 07:03 PM	08/Jan/07 02:39 AM
Bug	JBWS-1378	NPE with SOAP 1.2 WSDL	jbossws-1.2.0	Thomas Diesler	Thomas Diesler	Major	0	Open	UNRESOLVED	jaxrpc	15/Nov/06 08:05 PM	08/Jan/07 02:39 AM
Bug	JBWS-1259	stack-overflow when creating client for amazon webservices	jbossws-1.2.0	Thomas Diesler	Ole Matzura	Major	0	Open	UNRESOLVED	wstools	30/Sep/06 09:29 AM	08/Jan/07 02:40 AM
Bug	JBWS-1396	Now jbossws-beans is exploded jbossws.sar must be exploded	jbossws-1.2.0	Thomas Diesler	Darran Lofthouse	Major	0	Open	UNRESOLVED		22/Nov/06 09:57 AM	08/Jan/07 02:43 AM
Bug	JBWS-1414	Message style endpoints should never be registered as doc wrapped	jbossws-1.2.0	Thomas Diesler	Jason T. Greene	Major	0	Open	UNRESOLVED	jaxrpc	07/Dec/06 01:54 PM	08/Jan/07 02:45 AM
Generated at Mon Jan 08 03:10:30 EST 2007 by Thomas Diesler using JIRA 161.